## Dashboard
Project: Sustainable Shopping Assistant "Sift"
Project owner: Patrick Roennfeldt & Safin Ahmed
Total project duration | Overall completion | Days remaining
36 Days | 100% | 0
Tasks complete | Tasks in progress | Tasks not started
29 | 0 | 0

## Task Table
WBS # | Task Name | Start Date | End Date | Duration | % Complete | Completed | Remaining | Predecessor | Comments
1 | Analysis & Design Phase | 2026-07-20 | 2026-07-24 | 5 | 100% | 5 | 0
1.1 | Identify opportunity for innovation | 2026-07-20 | 2026-07-20 | 1 | 100% | 1 | 0
1.2 | Establish Gantt chart | 2026-07-21 | 2026-07-21 | 1 | 100% | 1 | 0 | 1.1
1.3 | Conduct user surveys | 2026-07-21 | 2026-07-21 | 1 | 100% | 1 | 0 | 1.2
1.4 | Document evaluation criteria | 2026-07-22 | 2026-07-22 | 1 | 100% | 1 | 0 | 1.3
1.5 | Identify emerging trends | 2026-07-22 | 2026-07-22 | 1 | 100% | 1 | 0 | 1.4
1.6 | Identify legal, economical and ethical considerations | 2026-07-22 | 2026-07-22 | 1 | 100% | 1 | 0 | 1.5
1.7 | Design the solution | 2026-07-23 | 2026-07-24 | 2 | 100% | 2 | 0 | 1.6
1.8 | Milestone: Analysis & Design complete | 2026-07-24 | 2026-07-24 | 1 | 100% | 1 | 0 | 1
2 | Design & Testing Phase | 2026-07-27 | 2026-07-29 | 3 | 100% | 3 | 0
2.1 | Develop a proof of concept | 2026-07-27 | 2026-07-27 | 1 | 100% | 1 | 0 | 1
2.2 | Document functions and techniques | 2026-07-27 | 2026-07-28 | 2 | 100% | 2 | 0 | 2.1
2.3 | Document testing methodology | 2026-07-28 | 2026-07-29 | 2 | 100% | 2 | 0 | 2.2
2.4 | Milestone: Design & Testing complete | 2026-07-29 | 2026-07-29 | 1 | 100% | 1 | 0 | 2
3 | Development & Coding Phase | 2026-07-30 | 2026-08-06 | 8 | 100% | 8 | 0
3.1 | Core code setup & UI skeleton | 2026-07-30 | 2026-08-04 | 6 | 100% | 6 | 0 | 2
3.2 | Calculation of data logic | 2026-08-04 | 2026-08-04 | 1 | 100% | 1 | 0 | 3.1
3.3 | UI and code structure integration | 2026-08-04 | 2026-08-05 | 2 | 100% | 2 | 0 | 3.2
3.4 | Technical documentation | 2026-07-30 | 2026-08-04 | 6 | 100% | 6 | 0 | 3
3.5 | Milestone: Development & Code complete | 2026-08-04 | 2026-08-06 | 3 | 100% | 3 | 0 | 3
4 | Testing & Refinement Phase | 2026-08-06 | 2026-08-10 | 5 | 100% | 5 | 0
4.1 | Create test case tables | 2026-08-06 | 2026-08-06 | 1 | 100% | 1 | 0 | 3
4.2 | Execute tests and resolve errors | 2026-08-06 | 2026-08-10 | 5 | 100% | 5 | 0 | 4.1
3.3 | Milestone: Testing & Refinement complete | 2026-08-10 | 2026-08-10 | 1 | 100% | 1 | 0 | 4
4 | Evaluation & Logs Phase | 2026-08-17 | 2026-08-24 | 8 | 100% | 8 | 0
4.1 | Write final evaluation report | 2026-08-17 | 2026-08-21 | 5 | 100% | 5 | 0 | 4
4.2 | Update and finalise project journal | 2026-08-17 | 2026-08-24 | 8 | 100% | 8 | 0 | 4
3.3 | Milestone: Evaluation & Logs complete | 2026-08-24 | 2026-08-24 | 1 | 100% | 1 | 0 | 4
5 | Due Date & Submission | 2026-08-17 | 2026-08-24 | 8 | 100% | 8 | 0